## Project 1- ColAlg&CS
ARC | TASK DESCRIPTION | PREDECESSOR(S) | PREDECESSOR(S) DESCRIPTION | DURATION (semesters) | OPTIMISTIC DURATION (semesters) | PESSIMISTIC DURATION (semesters) | CREDIT HOURS | OFFERED | CRITICAL
A | FAFSA Commitment* | None | None | 0.0625 | 0.0625 | 0.0625 | 0 | Fall, Spring, Summer | N
B | TSI Pre-Assessment Activity Certification | None | None | 0.00893 | 0.0625 | 0.0625 | 0 | Fall, Spring, Summer | Y
C | TSI Placement Exams | B | Pre-Assessment Activity | 0.0625 | 0.0625 | 0.0625 | 0 | Fall, Spring, Summer | Y
D | MATH 1301 | A, C | TSI Placement Exams | 1 | 0 | 2 | 3 | Fall, Spring, Summer | Y
E | MATH 1505 | D | MATH 1301 | 1 | 0 | 2 | 5 | Fall, Spring, Summer | Y
F | ENG 1301 | A, C | TSI Placement Exams | 1 | 0 | 2 | 3 | Fall, Spring, Summer | N
G | ENG 1302 | F | ENG 1301 | 1 | 0 | 2 | 3 | Fall, Spring, Summer | N
H | Core Components | A, C | co-req: ENG 1301 | 2* | 2 | 3 | 30 | Fall, Spring, Summer | N
I | CS 1311 | D | MATH 1301 | 1 | 1 | 2 | 3 | Fall, Spring, Summer | N
J | CS 2311 | I | CS 1311 | 1 | 1 | 2 | 3 | Fall, Spring | N
K | DATA 2401 | E | MATH 1505 | 1 | 1 | 2 | 4 | Fall, Spring | Y
L | DATA 3401 | I, K, O | CS 1311 & MATH 2305 & DATA 2401 | 1 | 1 | 2 | 4 | Fall, Spring | Y
M | DATA 3402 | J, L | CS 2311 & DATA 3401 | 1 | 1 | 2 | 4 | Fall, Spring | Y
N | DATA 4319 | I, L, Q. R | DATA 3401, co-req: MATH 3423 & STAT 3333 | 1 | 1 | 2 | 3 | Fall, Spring | Y
O | MATH 2305 | E | MATH 1505 | 1 | 1 | 2 | 3 | Fall, Spring, Summer | Y
P | MATH 2421 | E | MATH 1505 | 1 | 0 | 2 | 4 | Fall, Spring | Y
Q | MATH 2422 | P | MATH 2421 | 1 | 1 | 2 | 4 | Fall, Spring | Y
R | MATH 3302 | P | MATH 2421 | 1 | 1 | 2 | 3 | Fall, Spring, Summer | Y
S | MATH 3423 | I, Q | CS 1311 & MATH 2422 | 1 | 1 | 2 | 4 | Fall, Spring | Y
T | STAT 3333 | R | MATH 3302 | 1 | 1 | 2 | 3 | Fall, Spring | Y
U | STAT 4303 | R | MATH 3302 | 1 | 1 | 3 | 3 | A | Y
V | STAT 4310 | R | MATH 3302 | 1 | 1 | 3 | 3 | Spring only | Y
W | Achieve Senior Status | A, C | FAFSA, TSI Complete | 2* | 2* | 2* | 0 | N/A | N
X | Senior Project Approval | W | Achieve Senior Status | 1 | 1 | 1 | 0 | N/A | N
Y | Graduation Application | W | Achieve Senior Status | 1 | 1 | 1 | 0 | N/A | N
Z | DATA 4395 | X | Senior Project Approval | 1 | 1 | 2 | 3 | Fall, Spring, Summer | N
AA | DATA 4300 | L | DATA 3401 | 1 | 1 | 2 | 3 | Fall, Spring | Y
BB | PHIL 2305 | A, C | co-req: ENG 1301 | 1 | 1 | 2 | 3 | Fall, Spring, Summer | N
CC | CS 1410 | D | co-req: ENG 1301 & MATH 1505 | 1 | 0 | 2 | 4 | Fall, Spring, Summer | Y
DD | CS 2410 | E, CC | CS 1410, co-req: MATH 2421 | 1 | 1 | 2 | 4 | Fall, Spring, Summer | Y
EE | CS 3304 | O, DD | CS 2410 & MATH 2305 | 1 | 1 | 2 | 3 | Fall, Spring, Summer | Y
FF | CS 3321 | EE | CS 3304 | 1 | 1 | 2 | 3 | Fall, Spring | Y
GG | (Free Elective) SPAN 1401* | A, C | TSI Placement Exams | 1 | 0 | 2 | 4 | Fall, Spring, Summer | N
HH | (Free elective) SPAN 1402* | GG | SPAN 1402 | 1 | 0 | 2 | 4 | Fall, Spring, Summer | N
II | Commencement Ceremony | G, H, M, N, S, T, U, V, Y, Z, AA, BB, EE, FF, HH | All other tasks | 0.00893 | 0.00893 | 0.00893 | 0 | N/A | Y
|  |  |  | Total hours = |  |  | 123
FAFSA Commitment * This application has to happen before EACH academic year for which you're getting aid (fall semester)
Free Elective * May take other electives, does not have to be Spanish

## Project 2 - Precal&CS
ARC | TASK DESCRIPTION | PREDECESSOR(S) | PREDECESSOR(S) DESCRIPTION | DURATION (semesters) | OPTIMISTIC DURATION (semesters) | PESSIMISTIC DURATION (semesters) | CREDIT HOURS | OFFERED | CRITICAL
A | FAFSA Commitment* | None | None | 0.0625 | 0.0625 | 0.0625 | 0 | Fall, Spring, Summer | N
B | TSI Pre-Assessment Activity Certification | None | None | 0.00893 | 0.00893 | 0.00893 | 0 | Fall, Spring, Summer | Y
C | TSI Placement Exams | B | TSI Pre-Assessment Activity Certification | 0.0625 | 0.0625 | 0.0625 | 0 | Fall, Spring, Summer | Y
D | MATH 1301 Bypass Exam | A, C | TSI Placement Exams | 0.0625 | 0 | 0.0625 | 0 | Fall, Spring | Y
E | MATH 1505 | D | MATH 1301 Bypass Exam | 1 | 0 | 2 | 5 | Fall, Spring, Summer | Y
F | ENG 1301 | A, C | TSI Placement Exams | 1 | 0 | 2 | 3 | Fall, Spring, Summer | N
G | ENG 1302 | F | ENG 1301 | 1 | 0 | 2 | 3 | Fall, Spring, Summer | N
H | Core Component | A, C | TSI Placement Exams | 2* | 2 | 3 | 30 | Fall, Spring, Summer | N
I | CS 1311 | A, C | MATH 1301 Bypass Exam | 1 | 1 | 2 | 3 | Fall, Spring, Summer | N
J | CS 2311 | I | CS 1311 | 1 | 1 | 2 | 3 | Fall, Spring | N
K | DATA 2401 | E | MATH 1505 | 1 | 1 | 2 | 4 | Fall, Spring | Y
L | DATA 3401 | I, K, O | CS 1311 & MATH 2305 & DATA 2401 | 1 | 1 | 2 | 4 | Fall, Spring | Y
M | DATA 3402 | J, L | CS 2311 & DATA 3401 | 1 | 1 | 2 | 4 | Fall, Spring | Y
N | DATA 4319 | I, L, Q, R | DATA 3401, co-req: MATH 3423 & STAT 3333 | 1 | 1 | 2 | 3 | Fall, Spring | Y
O | MATH 2305 | E | MATH 1505 | 1 | 1 | 2 | 3 | Fall, Spring, Summer | Y
P | MATH 2421 | E | MATH 1505 | 1 | 0 | 2 | 4 | Fall, Spring | Y
Q | MATH 2422 | P | MATH 2421 | 1 | 1 | 2 | 4 | Fall, Spring | Y
R | MATH 3302 | P | MATH 2421 | 1 | 1 | 2 | 3 | Fall, Spring, Summer | Y
S | MATH 3423 | I, Q | CS 1311 & MATH 2422 | 1 | 1 | 2 | 4 | Fall, Spring | Y
T | STAT 3333 | R | MATH 3302 | 1 | 1 | 2 | 3 | Fall, Spring | Y
U | STAT 4303 | R | MATH 3302 | 1 | 1 | 3 | 3 | Fall only | Y
V | STAT 4310 | R | MATH 3302 | 1 | 1 | 3 | 3 | Spring only | Y
W | Achieve Senoir Status | A, C | FAFSA, TSI Complete | 2* | 2* | 2* | 0 | N/A | N
X | Senior Project Approval | W | Achieve Senior Status | 0.0625 | 0.0625 | 0.0625 | 0 | N/A | N
Y | Graduation Application | W | Achieve Senior Status | 0.0625 | 0.0625 | 0.0625 | 0 | N/A | N
Z | DATA 4395 | X | Senior Project Approval | 1 | 1 | 2 | 3 | Fall, Spring, Summer | N
AA | DATA 4300 | L | DATA 3401 | 1 | 1 | 2 | 3 | Fall, Spring | Y
BB | PHIL 2305 | A, C | co-req: ENG 1301 | 1 | 1 | 2 | 3 | Fall, Spring, Summer | N
CC | CS 1410 | D | co-req: ENG 1301 & MATH 1505 | 1 | 0 | 2 | 4 | Fall, Spring, Summer | Y
DD | CS 2410 | E, CC | CS 1410, co-req: MATH 2421 | 1 | 1 | 2 | 4 | Fall, Spring, Summer | Y
EE | CS 3304 | O, DD | CS 2410 & MATH 2305 | 1 | 1 | 2 | 3 | Fall, Spring, Summer | Y
FF | CS 3321 | EE | CS 3304 | 1 | 1 | 2 | 3 | Fall, Spring | Y
GG | (Free Elective) SPAN 1401* | A, C | TSI Placement Exams | 1 | 0 | 2 | 4 | Fall, Spring, Summer | N
HH | (Free elective) SPAN 1402* | GG | SPAN 1402 | 1 | 0 | 2 | 4 | Fall, Spring, Summer | N
II | Commencement Ceremony | G, H, M, N, S, T, U, V, Y, Z, AA, BB, EE, FF, HH | All other tasks | 0.00893 | 0.00893 | 0.00893 | 0 | N/A | Y
|  |  |  | Total hours = |  |  | 120
FAFSA Commitment * This application has to happen before EACH academic year for which you're getting aid (fall semester)
Free Elective * May take other electives, does not have to be Spanish

## Project 3 - Calc&CS
ARC | TASK DESCRIPTION | PREDECESSOR(S) | PREDECESSOR(S) DESCRIPTION | DURATION (Semesters) | OPTIMISTIC DURATION (semesters) | PESSIMISTIC DURATION (semesters) | CREDIT HOURS | OFFERED | CRITICAL
A | FAFSA Commitment* | None | None | 0.0625 | 0.0625 | 0.0625 | 0 | Fall, Spring, Summer | N
B | TSI Pre-Assessment Activity Certification | None | None | 0.00893 | 0.00893 | 0.00893 | 0 | Fall, Spring, Summer | Y
C | TSI Placement Exams | B | TSI Pre-Assessment Activity Certification | 0.0625 | 0.0625 | 0.0625 | 0 | Fall, Spring, Summer | Y
E | MATH 1505 Bypass Exam | A, C | TSI Placement Exams | 0.0625 | 0 | 2 | 0 | Fall, Spring | Y
F | ENG 1301 | A, C | TSI Placement Exams | 1 | 0 | 2 | 3 | Fall, Spring, Summer | N
G | ENG 1302 | F | ENG 1301 | 1 | 0 | 2 | 3 | Fall, Spring, Summer | N
H | Core Components | A, C | co-req: ENG 1301 | 2* | 2 | 3 | 30 | Fall, Spring, Summer | N
I | CS 1311 | A, C | MATH 1505 Bypass Exam | 1 | 1 | 2 | 3 | Fall, Spring, Summer | N
J | CS 2311 | I | CS 1311 | 1 | 1 | 2 | 3 | Fall, Spring | N
K | DATA 2401 | E | MATH 1505 Bypass Exam | 1 | 1 | 2 | 4 | Fall, Spring | Y
L | DATA 3401 | I, K, O | CS 1311 & MATH 2305 & DATA 2401 | 1 | 1 | 2 | 4 | Fall, Spring | Y
M | DATA 3402 | J, L | CS 2311 & DATA 3401 | 1 | 1 | 2 | 4 | Fall, Spring | Y
N | DATA 4319 | I, L, Q, R | DATA 3401, co-req: MATH 3423 & STAT 3333 | 1 | 1 | 2 | 3 | Fall, Spring | Y
O | MATH 2305 | E | MATH 1505 Bypass Exam | 1 | 1 | 2 | 3 | Fall, Spring, Summer | Y
P | MATH 2421 | E | MATH 1505 Bypass Exam | 1 | 0 | 2 | 4 | Fall, Spring | Y
Q | MATH 2422 | P | MATH 2421 | 1 | 1 | 2 | 4 | Fall, Spring | Y
R | MATH 3302 | P | MATH 2421 | 1 | 1 | 2 | 3 | Fall, Spring, Summer | Y
S | MATH 3423 | I, Q | CS 1311 & MATH 2422 | 1 | 1 | 2 | 4 | Fall, Spring | Y
T | STAT 3333 | R | MATH 3302 | 1 | 1 | 2 | 3 | Fall, Spring | Y
U | STAT 4303 | R | MATH 3302 | 1 | 1 | 3 | 3 | Fall only | Y
V | STAT 4310 | R | MATH 3302 | 1 | 1 | 3 | 3 | Spring only | Y
W | Achieve Senior Status | A, C | FAFSA, TSI Complete | 2* | 2* | 2* | 0 | N/A | N
X | Senior Project Approval | W | Achieve Senior Status | 0.0625 | 0.0625 | 0.0625 | 0 | N/A | N
Y | Graduation Application | W | Achieve Senior Status | 0.0625 | 0.0625 | 0.0625 | 0 | N/A | N
Z | DATA 4395 | X | Senior Project Approval | 1 | 1 | 2 | 3 | Fall, Spring, Summer | N
AA | DATA 4300 | L | DATA 3401 | 1 | 1 | 2 | 3 | Fall, Spring | Y
BB | PHIL 2305 | A, C | co-req: ENG 1301 | 1 | 1 | 2 | 3 | Fall, Spring, Summer | N
CC | CS 1410 | E | co-req: ENG 1301 & MATH 1505 | 1 | 0 | 2 | 4 | Fall, Spring, Summer | Y
DD | CS 2410 | CC | CS 1410, co-req: MATH 2421 | 1 | 1 | 2 | 4 | Fall, Spring, Summer | Y
EE | CS 3304 | O, DD | CS 2410 & MATH 2305 | 1 | 1 | 2 | 3 | Fall, Spring, Summer | Y
FF | CS 3321 | EE | CS 2410 & MATH 2305 | 1 | 1 | 2 | 3 | Fall, Spring | Y
GG | (Free Elective) SPAN 1401* | A, C | FAFSA, TSI Complete | 1 | 0 | 2 | 4 | Fall, Spring, Summer | N
HH | (Free elective) SPAN 1402* | GG | SPAN 1402 | 1 | 0 | 2 | 4 | Fall, Spring, Summer | N
JJ | Free Elective* | A, C | FAFSA, TSI Complete | 1 | 1 | 1 | 3 | Fall, Spring, Summer | N
KK | Free Elective* | A, C | FAFSA, TSI Complete | 1 | 1 | 1 | 3 | Fall, Spring, Summer | N
II | Commencement Ceremoy |  | All other tasks | 0.00893 | 0.00893 | 0.00893 | 0 | N/A | Y
|  |  |  | Total hours = | 121
FAFSA Commitment * This application has to happen before EACH academic year for which you're getting aid (fall semester)
Free Elective * May take other electives, does not have to be Spanish